# Beacon Week 1 Governance Package

Kestrel Health Network | Evidence status as of 8 December 2026

Sponsor decision: PAUSE / NO-GO for the 14 December pilot on current evidence. Network rollout on 11 January 2027 remains gated by pilot evidence and closure of network-scale controls.

Purpose: Provide a defensible, evidence-based package showing what is ready, what is not ready, who owns each decision, what evidence is required at each gate, and what must be resolved before Pilot and Network rollout.

Evidence discipline: Statements from chat or meetings are treated as claims unless supported by an approved, locatable artefact. Missing values are exposed as Unknown or Not met rather than invented.

# 1. Executive readiness decision

| Decision point | Recommendation | Basis |
| --- | --- | --- |
| 14 Dec 2026 Pilot - Riverside and Hillcrest | PAUSE / NO-GO | Current release candidate and configuration are not covered by the cited evaluation; clinical-safety, privacy, language-safety, retention, staffing and rollback controls remain open. |
| 11 Jan 2027 Network rollout - nine hospitals | NOT READY TO AUTHORIZE | Network rollout must depend on successful pilot evidence, approved scale criteria, model/version stability, drift evidence, trained staffing, incident response and closed governance controls. |

| # | Severity | Area | Finding | Category | Sponsor impact | Evidence reference | v1 replacement |
| --- | --- | --- | --- | --- | --- | --- | --- |
| F1 | Critical | Model evaluation / release candidate | Evaluation ev-118 covers build 1.4.0, while the current build is 1.4.2. | Evidence; Contradiction; Stage gate | The deployable build is not validated by the evidence being relied upon. | Part A4, current build; Part C1, evaluation footer; Part C2, build/configuration message | Run the full clinical evaluation on exact build 1.4.2 and bind report to build, prompt, model and configuration versions. |
| F2 | Critical | Confidence threshold | Evaluated/approved threshold was 0.80, but configuration was changed to 0.72 without required re-evaluation. | AI control; Evidence; Contradiction; Stage gate | Lowering the threshold expands autonomous routing using an unvalidated clinical operating point. | Part C1, evaluated threshold; Part C2, threshold-change message; AIP-2 | Restore 0.80 or complete required re-evaluation and obtain Clinical Safety Officer approval before pilot. |
| F3 | Critical | Mixed-language safety | Under-triage is 6.8% for mixed-language/transliterated messages versus 1.6% for English-only messages. | Dimension gap; Evidence | A materially worse result for a foreseeable patient group creates direct clinical harm risk. | Part C1, language-cohort evaluation results | Investigate, remediate and obtain approved clinical disposition; define pilot monitoring and stop criteria by language cohort. |
| F4 | Critical | Risk R-17 acceptance | Clinical risk was accepted by Neha Sharma although AIP-2 limits acceptance to the Chief Medical Officer or Clinical Safety Officer, in writing, with review date. | Ownership; Evidence; Contradiction | The purported acceptance is not by the authorized clinical authority and cannot close the gate. | Part C2, R-17 acceptance message; AIP-2 | Obtain written acceptance or rejection from an authorized CMO/CSO with residual risk, conditions and review/expiry date. |
| F5 | Critical | Clinical safety case | The claimed safety case is a supplier hazard log; Kestrel policy requires its own CSO-owned safety case. Dr. Helen Mathews has not reviewed it. | Ownership; Evidence; Contradiction | Supplier evidence alone does not demonstrate Kestrel-specific clinical hazards and controls. | Part B, clinical-safety checklist claim; Part C2, supplier hazard log / CSO review status; CSS-1 | Create and approve a Kestrel clinical safety case incorporating the supplier log as input, signed by Dr. Helen Mathews. |
| F6 | Critical | Privacy / DPIA scope | DPIA v1 covers referral letters but not patient-portal messages added later. | Dimension gap; Evidence; Stage gate | The actual pilot data flow is outside the approved privacy assessment. | Part C2, DPIA scope message; DPIA v1 | Update and approve the DPIA for portal messages, automated routing/advice, retention and human review before pilot. |
| F7 | Critical | Patient communications | Automated self-care replies average Grade 11 while PCS-3 requires Grade 8 or below; disclosure wording remains English-only. | Dimension gap; Evidence; Contradiction | Patients may misunderstand automated medical guidance and non-English users may not receive required disclosure. | Part C1, readability result; Part C2, disclosure wording; PCS-3 | Approve Grade 8-or-below content and required multilingual disclosure for all pilot channels. |
| F8 | Critical | Record retention | Configuration retains records for 365 days while RP-1 requires 8 years. | Evidence; Contradiction | Clinical decision evidence would be deleted long before the required retention period ends. | Part C2, retention configuration; RP-1 | Configure and verify 8-year retention for all required decision, model, prompt, routing and human-review records. |
| F9 | High | HITL urgent-case response | The stated urgent-case review target is 30 minutes, but staffing evidence indicates evening peak queues would take about 75 minutes to clear. | AI control; Dimension gap; Evidence; Contradiction | The human safety backstop cannot meet its promised response time during foreseeable peak demand. | Part B, 30-minute HITL target; Part C2, staffing/capacity message | Add staffing/capacity until 30-minute SLA is evidenced under peak load, or revise routing/automation and obtain clinical approval. |
| F10 | High | Training | Only 11 of 29 pilot nurses are trained (38%), although the inherited checklist says training is complete. | Dimension gap; Evidence; Contradiction | Untrained users may mishandle escalation, overrides and patient communication during pilot. | Part B #24; Part C2, training-status message | Complete role-based training and competency evidence for all pilot-shift personnel before activation. |
| F11 | High | Floating model alias | Production uses corvid-med-latest, scheduled to change to model 3.3 one day after pilot launch. | Stage gate; Evidence | The model can change after approval without a new gate, invalidating evaluation and safety evidence. | Part C2, model-alias configuration and provider-change message | Pin an approved model version and block unreviewed model changes; require re-evaluation before any version update. |
| F12 | High | Rollback coverage | Rollback runbook does not cover model rollback. | Evidence | The team may be unable to restore the clinically evaluated model if behavior deteriorates. | Part B, rollback checklist item; Part C2, rollback runbook scope | Rehearse rollback of application, prompt, model and configuration; record versions, duration and result. |
| F13 | High | Model drift monitoring | No complete clinical drift control is evidenced for under-triage, category distribution, language cohorts and overrides. | AI control; Dimension gap; Evidence | Clinical quality can deteriorate while infrastructure remains healthy. | Part C3, monitoring summary | Define baseline, acceptable bands, alerts, named responder and automatic pause/rollback action for clinical model behavior. |
| F14 | High | Pilot abort criteria | Pilot stop/abort thresholds are not evidenced for clinical error, SLA breach, unsafe advice or monitoring failure. | Dimension gap; AI control; Evidence | The sponsor lacks a predetermined rule for containing patient harm during pilot. | Part B, Pilot plan; Part C3, missing abort-control evidence | Define measurable pilot success and abort criteria, authority, evidence cadence and stop mechanism before activation. |
| F15 | High | Phase separation | Pilot readiness and nine-hospital network readiness are not clearly separated in the inherited checklist. | Dimension gap; Stage gate | A limited pilot could be mistaken for evidence that network-scale capacity and controls are ready. | Part A2, two-phase rollout; Part B, inherited checklist structure | Create separate Pilot and Network gates; network approval must require successful pilot report and scale-specific evidence. |
| F16 | High | Auditability | Decision records are not demonstrated to bind message, category, confidence, model, prompt/configuration, advice, override and reviewer. | Dimension gap; Evidence | Kestrel may be unable to reconstruct a patient-triage decision after an incident. | Part C3, logging and retention summary | Define and sample-test a complete clinical decision audit record with 8-year retention. |
| F17 | Medium | Network capacity | Evidence for all-nine-hospital workload, on-call, training and support is not yet established. | Dimension gap; Evidence | A two-site pilot cannot prove network-scale operational readiness. | Part A2, Network rollout scope; Part C2, network-readiness evidence | Require network load test, staffing, rota, training and incident-readiness evidence before 11 January gate. |
| F18 | Medium | Go/No-Go role | The final meeting must not be the first point where open controls are reviewed. | Stage gate | Late discovery encourages unsupported acceptance under schedule pressure. | Part B, inherited gate design; Part E, task and ground rules | Require each stage gate to pass with logged evidence; final Go/No-Go only confirms completed gates and decides release. |

# 2. Governance frame

The ownership model below uses only the named Kestrel personnel permitted by Section A3. Each readiness dimension has exactly one named Accountable person. Teams, suppliers, departed personnel and invented people are not used as owners.

| Dimension | Accountable | Responsible | Consulted | Informed | Why this owner |
| --- | --- | --- | --- | --- | --- |
| Business | Marcus Bell, Chief Digital Officer | Neha Sharma, Delivery Lead | Dr. Anjali Rao, Chief Medical Officer / Sponsor; Priyanka Das, Head of Nursing; Sunil Bhat, Patient Contact Centre Manager | Victor Osei, QA Manager; Kavya Nair, Platform & SRE Lead | Marcus Bell owns Beacon's business case and budget, so Marcus Bell is the clearest single Accountable owner for whether Beacon delivers the intended business outcome. |
| Technical | Neha Sharma, Delivery Lead, Beacon | Imran Qureshi, Lead Engineer / Agent Orchestrator; Tobias Grant, Solution Architect | Rahul Menon, CISO; Kavya Nair, Platform & SRE Lead; Dr. Helen Mathews, CSO | Dr. Anjali Rao; Marcus Bell; Victor Osei | Neha Sharma runs the Beacon delivery team, making Neha Sharma the strongest continuing Kestrel owner for the overall technical delivery outcome. Tobias Grant designed the integration architecture but is a contractor whose contract ends on 18 December, so Tobias Grant should not carry lasting technical accountability into the network rollout. |
| Quality | Victor Osei, QA Manager | Dr. Farah Siddiqui, Head of Data & AI; Imran Qureshi, Lead Engineer / Agent Orchestrator | Dr. Helen Mathews, CSO; Priyanka Das, Head of Nursing | Dr. Anjali Rao; Marcus Bell; Neha Sharma | Victor Osei owns the test strategy from November 2026, so Victor Osei should be accountable for whether the release candidate has sufficient, current and representative quality evidence. Dr. Farah Siddiqui remains Responsible for the AI evaluation because Dr. Farah Siddiqui built Kestrel's evaluation set and ran the internal evaluation. |
| Governance | Dr. Helen Mathews, Clinical Safety Officer | Owen Fletcher, Head of Risk & Compliance; Grace Liu, DPO; Rahul Menon, CISO | Dr. Anjali Rao, Chief Medical Officer; Dr. Farah Siddiqui, Head of Data & AI; Victor Osei, QA Manager | Marcus Bell; Neha Sharma; Kavya Nair | Dr. Helen Mathews owns Kestrel's Clinical Safety Standard, and CSS-1 requires a Kestrel clinical safety case owned and signed by Kestrel's CSO. AIP-2 also permits clinical AI risk acceptance only by the CMO or CSO. This makes Dr. Helen Mathews the strongest single Governance Accountable. |
| Operational | Kavya Nair, Platform & SRE Lead | Priyanka Das, Head of Nursing; Sunil Bhat, Patient Contact Centre Manager | Neha Sharma, Delivery Lead; Dr. Helen Mathews, CSO; Victor Osei, QA Manager; Imran Qureshi, Lead Engineer / Agent Orchestrator | Dr. Anjali Rao; Marcus Bell | Kavya Nair owns hosting, monitoring, alerting and the platform on-call rota, making Kavya Nair the clearest single Accountable owner for Beacon's production-operability dimension. Priyanka Das remains Responsible for the clinical/nursing operating path because Priyanka Das manages the triage nurses receiving cases Beacon does not route automatically. |

# 3. Stage-gate map

| Dimension | Intent | Spec | Plan | Build | Review | Deploy |
| --- | --- | --- | --- | --- | --- | --- |
| Business | Approver: Marcus Bell · Artefact: signed Pilot and Network outcome charter |  | Approver: Marcus Bell · Artefact: approved phase plan with success and abort criteria |  | Approver: Marcus Bell · Artefact: Pilot outcome and scale-readiness report | Approver: Dr. Anjali Rao · Artefact: signed Pilot or Network Go/No-Go record |
| Technical |  | Approver: Tobias Grant · Artefact: approved architecture, pinned-model and data-flow specification | Approver: Neha Sharma · Artefact: implementation, dependency and rollback plan |  | Approver: Neha Sharma · Artefact: release manifest linking build, model, prompt, threshold and configuration | Approver: Kavya Nair · Artefact: deployment verification and successful rollback-rehearsal record |
| Quality |  | Approver: Victor Osei · Artefact: evaluation plan and acceptance criteria |  | Approver: Victor Osei · Artefact: signed evaluation report for the exact release candidate | Approver: Dr. Helen Mathews · Artefact: clinical, subgroup, language, UAT and regression evidence pack | Approver: Victor Osei · Artefact: production-candidate-to-evaluation traceability record |
| Governance |  | Approver: Dr. Helen Mathews · Artefact: approved clinical-safety, AI-control, privacy and records requirements |  |  | Approver: Dr. Helen Mathews · Artefact: Kestrel safety case, DPIA, risk dispositions and patient-content approvals | Approver: Dr. Helen Mathews · Artefact: signed governance gate confirmation |
| Operational |  | Approver: Priyanka Das · Artefact: HITL workflow, 30-minute SLA and staffing requirements | Approver: Kavya Nair · Artefact: Pilot operations, monitoring, incident and rollout plan |  | Approver: Priyanka Das · Artefact: training, queue/load, UAT and clinical-operations readiness evidence | Approver: Kavya Nair · Artefact: live monitoring, on-call, incident drill and controlled activation record |

Purpose of final Go/No-Go: confirm that all required Pilot or Network stage gates have already passed with recorded evidence and make the release decision; it is not the first point at which readiness controls are checked.

# 4. Release-Readiness Checklist v1

| ID | Stage | Dim. | Gate | Checkable criterion | Evidence | Where logged | Accountable | Approver | Status at 8 Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AI-01 | Review | Governance | Pilot | Is Beacon's confidence-score threshold fixed at 0.80, as evaluated in ev-118, with the threshold source documented, cases below the threshold routed to human review, and any threshold change re-evaluated and clinically approved under AIP-2? | ev-118 showing evaluated threshold; runtime configuration; threshold-change approval/re-evaluation | AI control register + deployment manifest | Dr. Helen Mathews, Clinical Safety Officer | Dr. Helen Mathews, Clinical Safety Officer, under AIP-2 | Not met: the evaluated threshold is 0.80, but runtime configuration is 0.72; the required re-evaluation and clinical approval for that change are not evidenced. |
| AI-02 | Spec / Deploy | Operational | Pilot | Are Emergency/Urgent classifications, low-confidence cases and other defined clinical exceptions routed to a Kestrel triage nurse under Priyanka Das within 30 minutes, with peak-load evidence demonstrating that SLA can be met? | HITL workflow; approved 30-minute SLA; peak staffing/queue evidence | Clinical operations register | Kavya Nair, Platform & SRE Lead | Dr. Helen Mathews, Clinical Safety Officer | Not met: a 30-minute human-review target exists, but staffing evidence indicates approximately 75 minutes to clear the evening peak queue. |
| AI-03 | Spec / Deploy | Operational | Pilot + Network | Are under-triage, category/confidence distributions, language-cohort results and human overrides monitored against an approved baseline and operating band, with an alert destination, named responder and enforced pause/escalation action on breach? | Monitoring specification; approved baseline/bands; alert configuration and test; response procedure | Monitoring + incident register | Kavya Nair, Platform & SRE Lead | Dr. Helen Mathews, Clinical Safety Officer | Not met: the supplied evidence does not demonstrate a complete clinical drift control with approved model-behaviour baselines/bands, alerts and breach actions. |
| B-01 | Intent | Business | Pilot | Are Pilot scope, business success metrics and measurable patient-safety abort criteria approved before Pilot activation? | Signed Pilot charter including success and abort criteria | Programme decision register | Marcus Bell, Chief Digital Officer | Dr. Anjali Rao, Chief Medical Officer / Programme Sponsor | Not met: Pilot scope exists, but measurable safety abort criteria and their approval are not evidenced. |
| B-02 | Intent | Business | Network | Are Network success, safety, capacity and scale-out criteria separately defined and approved rather than inferred from Pilot readiness? | Approved Network rollout charter | Programme decision register | Marcus Bell, Chief Digital Officer | Dr. Anjali Rao, Chief Medical Officer / Programme Sponsor | Unknown: the Network rollout is defined, but approved Network-specific success/safety/capacity criteria are not evidenced as of 8 Dec. |
| B-03 | Deploy | Business | Pilot | Has the Pilot Go/No-Go been approved only after all mandatory Pilot stage gates have passed or any policy-permitted residual risks have been formally accepted by authorized persons? | Signed Pilot Go/No-Go record + gate evidence pack | Decision register | Marcus Bell, Chief Digital Officer | Dr. Anjali Rao, Chief Medical Officer / Programme Sponsor | Not met: multiple mandatory Quality, Governance, Technical and Operational Pilot gates remain open. |
| B-04 | Review | Business | Network | Does a signed Pilot outcome report demonstrate achievement of the pre-approved Pilot success/abort criteria and closure/disposition of conditions for network scale-out? | Signed Pilot outcome report | Programme evidence repository | Marcus Bell, Chief Digital Officer | Dr. Anjali Rao, Chief Medical Officer / Programme Sponsor | Unknown: the Pilot has not occurred as of 8 Dec, so Pilot outcome evidence cannot yet exist. |
| T-01 | Spec | Technical | Pilot | Is the production model pinned to the exact evaluated and approved model version rather than a floating alias? | Approved technical specification; deployment configuration; model-version manifest | Architecture/configuration register | Neha Sharma, Delivery Lead, Beacon | Tobias Grant, Solution Architect | Not met: production uses corvid-med-latest, allowing the underlying model to change after approval and potentially invalidate existing evidence. |
| T-02 | Build | Technical | Pilot | Does release build 1.4.2, including model, prompt, threshold and configuration, exactly match the candidate covered by release evaluation evidence? | Build/release manifest linked to evaluation artefact | CI/CD release record | Neha Sharma, Delivery Lead, Beacon | Victor Osei, QA Manager | Not met: ev-118 covers build 1.4.0 and the evaluated 0.80 threshold, while the current release candidate/configuration differs. |
| T-03 | Deploy | Technical | Pilot | Has rollback of the application, prompt, model and configuration been successfully rehearsed for the intended Pilot release? | Dated rollback drill identifying versions restored, operator, result and recovery time | Runbook + change register | Neha Sharma, Delivery Lead, Beacon | Kavya Nair, Platform & SRE Lead | Not met: the supplied rollback procedure does not cover model rollback; therefore full-stack rollback has not been demonstrated. |
| T-04 | Plan / Deploy | Technical | Network | Have nine-hospital capacity, dependencies, failover and recovery been tested against the Network rollout design? | Network load/failover/recovery report | Technical readiness register | Neha Sharma, Delivery Lead, Beacon | Kavya Nair, Platform & SRE Lead | Unknown: network-scale technical evidence is not established as of 8 Dec and is not demonstrated by the two-site Pilot design. |
| Q-01 | Build | Quality | Pilot | Has the complete clinical evaluation suite been executed on the exact build 1.4.2 and intended runtime configuration, including the production threshold/model? | Signed evaluation report tied to release manifest | Evaluation repository | Victor Osei, QA Manager | Dr. Helen Mathews, Clinical Safety Officer | Not met: the available evaluation covers build 1.4.0 and does not validate the current build/configuration intended for Pilot. |
| Q-02 | Review | Quality | Pilot | Has the 6.8% mixed-language/transliterated under-triage result versus 1.6% English-only been investigated, remediated/re-evaluated, or formally dispositioned by authorized clinical authority? | Language-cohort evaluation; investigation/remediation report; authorized risk disposition if applicable | Clinical safety register | Victor Osei, QA Manager | Dr. Helen Mathews, Clinical Safety Officer | Not met: the material subgroup difference remains unresolved and the existing attempted acceptance is not by an AIP-2-authorized accepter. |
| Q-03 | Review | Quality | Pilot | Do all automated Self-care patient messages satisfy PCS-3 readability and required disclosure criteria for every applicable Pilot language/channel? | Release-candidate readability results + approved multilingual content/disclosure pack | Patient communications register | Victor Osei, QA Manager | Dr. Helen Mathews, Clinical Safety Officer | Not met: Self-care messages average Grade 11 versus the Grade 8 requirement, and disclosure remains English-only. |
| Q-04 | Review | Quality | Pilot | Has representative clinical-user UAT covered normal cases, peak-load workflow, HITL handoffs, overrides and unsafe/incorrect-output scenarios? | Signed UAT report, participants, defects and dispositions | Quality register | Victor Osei, QA Manager | Priyanka Das, Head of Nursing | Unknown: sufficient representative UAT evidence covering these scenarios is not established in the supplied evidence. |
| Q-05 | Review | Quality | Network | After Pilot changes, has a network-representative regression/evaluation suite passed on the exact Network release candidate? | Signed Network regression/evaluation report | Evaluation repository | Victor Osei, QA Manager | Dr. Helen Mathews, Clinical Safety Officer | Unknown: the Pilot has not yet occurred and therefore the final Network release candidate and post-Pilot regression evidence do not yet exist. |
| G-01 | Review | Governance | Pilot | Has Kestrel produced its own CSS-1-compliant clinical safety case, using supplier material only as input, with review and sign-off by Kestrel's CSO? | Signed Kestrel clinical safety case | Clinical safety register | Dr. Helen Mathews, Clinical Safety Officer | Dr. Helen Mathews, under CSS-1; signed safety case provided to Dr. Anjali Rao for Pilot Go/No-Go | Not met: the available artefact is the supplier hazard log; the required Kestrel CSO-owned safety case and CSO review are not evidenced. |
| G-02 | Review | Governance | Pilot | Has the DPIA been updated and approved for the actual Pilot scope, including portal messages and automated AI routing/advice? | Approved updated DPIA | Privacy register | Dr. Helen Mathews, Clinical Safety Officer | Grace Liu, Data Protection Officer | Not met: the available DPIA covers the earlier referral-letter scope and does not cover the expanded portal-message processing. |
| G-03 | Review | Governance | Pilot | If risk R-17 remains open after remediation, has residual clinical AI risk been accepted only by an AIP-2-authorized CMO/CSO, in writing, with rationale, conditions and review date? | Signed risk-acceptance record | Clinical risk register | Dr. Helen Mathews, Clinical Safety Officer | Approver: Dr. Helen Mathews, Clinical Safety Officer under AIP-2; Dr. Anjali Rao receives the disposition for Pilot Go/No-Go as permitted by AIP-2 | Not met: the current acceptance by Neha Sharma does not satisfy AIP-2 authorization requirements. |
| G-04 | Deploy | Governance | Pilot + Network | Are all required clinical decision and supporting governance records configured and verified for eight-year retention under RP-1? | Retention configuration + sample retained/exported decision record | Records/audit register | Dr. Helen Mathews, Clinical Safety Officer | Grace Liu, Data Protection Officer | Not met: current configuration retains records for 365 days rather than the required eight years. |
| G-05 | Review | Governance | Pilot | Have automated patient advice and AI disclosures been approved for all languages and delivery channels in the Pilot scope? | Final approved patient-content/disclosure pack | Patient communications register | Dr. Helen Mathews, Clinical Safety Officer | Owen Fletcher, Head of Risk & Compliance | Not met: the available evidence shows unresolved readability requirements and English-only disclosure. |
| G-06 | Review | Governance | Network | Before scale-out, have all Pilot incidents, safety findings, overrides and accepted residual risks been reviewed and dispositioned by the authorized governance/clinical authorities? | Signed Network risk review linked to Pilot incident and safety evidence | Clinical risk register | Dr. Helen Mathews, Clinical Safety Officer | Dr. Anjali Rao, Chief Medical Officer / Programme Sponsor | Unknown: Pilot operational evidence does not yet exist as of 8 Dec. |
| O-01 | Deploy | Operational | Pilot | Has Priyanka Das confirmed through the training register that all nurses assigned to Pilot shifts completed Beacon training and competency assessment before Kavya Nair activates the operational gate? | Training roster + competency/completion records mapped to Pilot shifts | Training register | Kavya Nair, Platform & SRE Lead | Priyanka Das, Head of Nursing | Not met: only 11 of 29 Pilot nurses, 38%, are recorded as trained. |
| O-02 | Review / Deploy | Operational | Pilot | Can planned clinical staffing meet the 30-minute urgent human-review target under expected evening peak volume? | Queue/capacity simulation + approved staffing schedule | Operations capacity register | Kavya Nair, Platform & SRE Lead | Priyanka Das, Head of Nursing | Not met: staffing evidence indicates approximately 75 minutes to clear the evening peak queue, materially exceeding the target. |
| O-03 | Deploy | Operational | Pilot | Are the Pilot on-call rota, AI-specific incident runbook, alert routes, stop controls, and full rollback procedures for the application, prompt, model and configuration live and successfully tested before activation? | Named on-call rota; alert/incident drill results; AI incident runbook; stop-control test; full rollback rehearsal record | Operations register | Kavya Nair, Platform & SRE Lead | Dr. Helen Mathews, Clinical Safety Officer | Not met: the rollback procedure does not cover model rollback, and the supplied evidence does not demonstrate that the complete AI incident, alert, stop and full-stack rollback controls have been successfully tested. |
| O-04 | Deploy | Operational | Pilot | Is Pilot exposure restricted to Riverside and Hillcrest, with named stop authority, defined daily evidence review and an enforceable mechanism to pause the Pilot if abort criteria are breached? | Pilot activation plan + control dashboard + stop-authority record | Pilot operations register | Kavya Nair, Platform & SRE Lead | Dr. Anjali Rao, Chief Medical Officer / Programme Sponsor | Unknown: the two-site Pilot scope is defined, but complete stop-authority, daily-review and enforceable-abort evidence is not established. |
| O-05 | Plan / Deploy | Operational | Network | Are training, staffing, support, monitoring, incident response and on-call coverage ready across all nine hospitals before Network activation? | Network operational-readiness pack | Network operations register | Kavya Nair, Platform & SRE Lead | Dr. Anjali Rao, Chief Medical Officer / Programme Sponsor | Unknown: the required Network-scale operational evidence is not yet available and must be demonstrated before the 11 January gate. |
| O-06 | Review | Operational | Network | Has the Pilot produced sufficient monitored evidence over the approved observation period to demonstrate stable clinical performance, HITL SLA achievement, acceptable language-cohort behavior, safe overrides and manageable incident rates? | Signed Pilot monitoring/outcome report | Monitoring register | Kavya Nair, Platform & SRE Lead | Dr. Helen Mathews, Clinical Safety Officer | Unknown: the Pilot has not yet occurred; therefore evidence required to authorize Network scale-out cannot yet exist. |

# 5. Level 4 open-control and risk-acceptance register

| ID | Open contradiction/deferred control | Status | Gate action | Closure or exception rule | Owner | Authorized approver / risk accepter where policy permits | Log |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RA-01 | Threshold 0.72 vs evaluated 0.80 | Not met | Block autonomous Pilot configuration | Restore the evaluated 0.80 threshold, or re-evaluate 0.72 and obtain required clinical approval. Schedule pressure cannot substitute for evaluation. | Dr. Farah Siddiqui, Head of Data & AI | Dr. Helen Mathews, Clinical Safety Officer | AI control register + clinical risk register |
| RA-02 | Mixed-language/transliterated under-triage 6.8% vs 1.6% English-only | Not met | Pause affected Pilot use | Remediate and re-evaluate; if residual clinical risk is to be accepted, AIP-2 requires written acceptance with conditions/review date by authorized clinical authority. | Victor Osei, QA Manager | Dr. Anjali Rao, Chief Medical Officer OR Dr. Helen Mathews, Clinical Safety Officer | Clinical risk register |
| RA-03 | Supplier hazard log substituted for Kestrel's required clinical safety case | Not met | Block Pilot | Produce Kestrel's own clinical safety case using the supplier hazard log only as an input; obtain CSO review/sign-off. | Dr. Helen Mathews, Clinical Safety Officer | Dr. Helen Mathews, Clinical Safety Officer | Clinical safety register |
| RA-04 | DPIA excludes patient-portal-message scope added later | Not met | Block affected processing / Pilot gate | Update the DPIA to cover portal messages, AI routing/advice, human review and applicable data flows; obtain privacy approval. Do not infer an exception. | Grace Liu, Data Protection Officer | Grace Liu, Data Protection Officer | Privacy / DPIA register |
| RA-05 | Retention configured for 365 days vs RP-1 requirement of 8 years | Not met | Block Pilot | Correct the retention configuration to eight years and verify it using configuration/sample evidence. Do not treat this configuration contradiction as accepted risk without explicit applicable authority. | Grace Liu, Data Protection Officer | Owen Fletcher, Head of Risk & Compliance for governance closure; any formal policy exception requires separately evidenced authority | Records / compliance risk register |
| RA-06 | Urgent human-review target is 30 minutes, but peak staffing evidence indicates approximately 75 minutes | Not met | Pause / restrict Pilot | Increase clinical-review capacity or redesign routing until the 30-minute control is demonstrated under peak conditions. Any residual clinical risk exception must follow AIP-2. | Priyanka Das, Head of Nursing | Dr. Anjali Rao, CMO OR Dr. Helen Mathews, CSO for clinical risk acceptance | Operations + clinical risk register |
| RA-07 | Production uses floating alias corvid-med-latest, which can change after approval | Not met | Block deployment | Pin the evaluated/approved model version. Any subsequent model change must trigger the appropriate change gate, evaluation and clinical approval before use. | Neha Sharma, Delivery Lead | Dr. Helen Mathews, Clinical Safety Officer for AI/clinical gate; Tobias Grant, Solution Architect consulted on architecture | Change + AI control register |
| RA-08 | Rollback runbook excludes model rollback | Not met | Pause deployment | Add application + prompt + model + configuration rollback, rehearse it, and retain evidence of versions restored, operator, outcome and recovery time. | Kavya Nair, Platform & SRE Lead | Neha Sharma, Delivery Lead, with clinical readiness confirmed by Dr. Helen Mathews where rollback changes clinical AI behavior | Runbook / change / operational risk register |

Risk-acceptance rule: an open criterion remains open. An exception may be used only where policy permits and the record states residual risk, rationale, compensating controls, named authorized accepter, date, conditions and review/expiry. Schedule pressure is not risk acceptance.

# 6. Readiness statement to the sponsor

| Heading | Statement |
| --- | --- |
| To | Dr. Anjali Rao, Chief Medical Officer / Programme Sponsor, Kestrel Health Network |
| What is ready | Beacon has a defined two-site Pilot, a functioning build, an evaluation artefact and documented workflows. These demonstrate progress but do not validate build 1.4.2 and its production configuration. |
| What is not ready | The evaluated build and threshold differ from production; mixed-language under-triage remains unresolved; clinical-risk acceptance is unauthorized; the Kestrel safety case and DPIA are incomplete; patient advice fails readability/disclosure requirements; retention is 365 days rather than eight years; only 11 of 29 nurses are trained; peak human review exceeds the 30-minute target; the model is not pinned; and rollback excludes the model. |
| What must happen before the 14 December Pilot | Evaluate exact build 1.4.2 and its runtime configuration; resolve subgroup safety issues; approve the Kestrel safety case, DPIA and patient content; pin the model; configure eight-year retention; complete training and staffing; activate HITL/drift controls and abort criteria; and rehearse full rollback. |
| What is additionally required before the 11 January Network rollout | Require a signed Pilot outcome report plus nine-hospital capacity, training, on-call, privacy, records, support and regression evidence for the final Network release candidate. |
| Recommendation | PAUSE / NO-GO for the 14 December Pilot. The Pilot may proceed only after material gates are evidenced, logged and approved. Network rollout remains a separate decision and cannot be authorized solely because a limited Pilot has started. |

# 7. Assumptions and evidence limitations

| # | Assumption / limitation | Treatment |
| --- | --- | --- |
| A1 | No missing HITL response-time, drift tolerance band, clinical-performance tolerance, or other control value has been invented; where the case supplies a value such as the 30-minute target, that value is used. | Where the Scenario Pack does not provide an approved value, the criterion remains Not met / Unknown until the appropriate named authority defines and approves it. |
| A2 | A Teams/chat statement is treated as a claim, not sufficient evidence by itself. | A gate remains open until the required approved and locatable artefact supports the claim. |
| A3 | The two-site Pilot does not demonstrate readiness for the nine-hospital Network rollout. | Pilot and Network are treated as separate release gates. The 11 January Network decision requires successful Pilot evidence plus network-scale readiness evidence. |
| A4 | A documented procedure is not treated as evidence that the procedure works. | Controls such as rollback, recovery, monitoring and incident handling require execution/rehearsal evidence where applicable. |
| A5 | No authority to accept or waive a risk has been inferred from job seniority. | Risk acceptance is recognized only where the case/policy establishes the authority. For clinical AI risk under AIP-2, acceptance must come from the authorized Chief Medical Officer or Clinical Safety Officer, with the required written record and review conditions. |